## Assest List
Asset List
|  | Script | 2D Art | 3D Art | UV Maps | Completed | Date Completed | Date Started | Date Expected | Notes
Resources Needed
| Models | [7 empty] | Dec 04, 2018
| Scripting | [7 empty] | Dec 04, 2018
| Sounds | [7 empty] | Dec 04, 2018
| History/Resources | [7 empty] | Sep 20, 2018
| Enviroment | [7 empty] | Dec 04, 2018
| Special Effects | [7 empty] | Dec 04, 2018
Models
| Parthenon Vanilla | [7 empty] | Nov 11, 2018
| Parthenon Modern | [7 empty] | Nov 04, 2018
| Statue of Athena | [7 empty] | Oct 25, 2018
| Statues Front Entrance | [7 empty] | Nov 18, 2018
| Statues Back Entrance | [7 empty] | Nov 18, 2018
Scripting
| Main Page UI | [7 empty] | Oct 18, 2018
| Camera Movement coding | [7 empty] | Oct 18, 2018
| Information UI | [7 empty] | Oct 18, 2018
| Sound UI | [7 empty] | Oct 18, 2018
| Scrolling UI | [7 empty] | Oct 18, 2018
Sounds
| Breeze | [7 empty] | Oct 11,2018
| Daytime noise | [7 empty] | Oct 11,2018
| Fire crakling | [7 empty] | Oct 11,2018
| Night Time Noise | [7 empty] | Oct 11,2018
| Dust falling | [7 empty] | Oct 11,2018
| Bird Chirpping | [7 empty] | Oct 11,2018
| Wind | [7 empty] | Oct 11,2018
| Thunder/Lightning | [7 empty] | Oct 11,2018
History/ Resources
| History of the Parthenon | [7 empty] | Sep 20, 2018
| Myth Athena & Posiedon | [7 empty] | Sep 20, 2018
| Myth Birth of Athena | [7 empty] | Sep 20, 2018
| Recent Progress/ News | [7 empty] | Sep 20, 2018
| Any other Myths involved | [7 empty] | Sep 20, 2018
Enviroment
| Grass | [7 empty] | Nov 25, 2018
| Rocks | [7 empty] | Nov 25, 2018
| Stones | [7 empty] | Nov 25, 2018
| Trees | [7 empty] | Nov 25, 2018
| Clouds | [7 empty] | Nov 25, 2018
Special Effects
| Lighting | [7 empty] | Nov 25, 2018
| Fire | [7 empty] | Nov 25, 2018
| Rain | [7 empty] | Nov 25, 2018
| Lightning | [7 empty] | Nov 25, 2018

## Schedule
Schedule
September
| Mondy | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 3 | 4 | 5 | 6 | 7 | 8 | 9
|  |  |  | Turn in Project Proposal | Begin Modeling/
Unity Build
| 10 | 11 | 12 | 13 | 14 | 15 | 16
| 17 | 18 | 19 | 20 | 21 | 22 | 23
Have history/resources
completed
| 24 | 25 | 26 | 27 | 28 | 29 | 30
October
| 1 | 2 | 3 | 4 | 5 | 6 | 7
| 8 | 9 | 10 | 11 | 12 | 13 | 14
Sound Completed
| 15 | 16 | 17 | 18 | 19 | 20 | 21
Scripting/UI Completed
| 22 | 23 | 24 | 25 | 26 | 27 | 28
Statue of Athena
completed
| 29 | 30 | 31
November
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Parthenon modern
completed
| 8 | 9 | 10 | 11 | 12 | 13 | 14
Parthenon Vanilla
| 15 | 16 | 17 | 18 | 19 | 20 | 21
Statues for both Entrance
and back completed
| 22 | 23 | 24 | 25 | 26 | 27 | 28
Enviorments/ Special
effects completed
| 29 | 30
December
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Prototype finished
| 8 | 9 | 10
End of the semester

## Videos for resources
https://www.youtube.com/watch?v=8KA0C26Vzs8
https://www.youtube.com/watch?v=TJ7dYIi3RI4
https://www.youtube.com/watch?v=J3MXPqYKKRM